## Slide 1: Proxy Micronutrient Deficiency Prediction Project: Progress Update
Andrew N. Mertens, UC Berkeley

## Slide 2: Overview

## Slide 3
Aim: Develop models to estimate global, national and sub‑national prevalence of micronutrient deficiencies using proxy indicators
Current focus micronutrients: iron, vitamin A, zinc, iodine, folate
Phases
  Conceptual frameworks + data landscape
  Proof‑of‑concept model development (West Africa)
  Expansion (contingent on Phase 2 success)

## Slide 4: Milestones

## Slide 5
Deliverable | Target | Status
Scientific Advisory Board | Feb 2024 | ✅ established
Draft analysis plan | Mar 2024 | ✅ complete
Conceptual frameworks (4 MN) | Apr 2024 | ✅ drafts reviewed
Landscaping analysis | Apr 2024 | 🟢 near final
Compiled datasets (2 data‑rich) | Dec 2024 | 🟡 in progress
Compiled datasets (3‑4 constrained) | Jun 2025 | ⏳ not started

## Slide 6: Data landscape snapshot

## Slide 7
# TODO: Insert code to read `data_landscape_type1.csv` # and plot availability heatmap (Figure 1 placeholder)
Figure 1 placeholder for Type 1 coverage by country‑year. See Manus_data sources landscape_2025 draft.

## Slide 8: Micronutrient survey coverage

## Slide 9
# TODO: Plot DHS indicator domain coverage (Figure 2 placeholder)

## Slide 10: Predictor data aggregation workflow

## Slide 11
# load core packages library(tidyverse) library(sf) library(terra) library(SuperLearner) # source utility functions #source("R/dhs_surface.R")
Steps 1. Import national surveys (DHS/MICS, BRINDA, HCES) 2. Join annual modeled series (IHME, FAO SUA/FBS, JMP WASH) 3. Rasterize and aggregate remote‑sensed covariates (MAP, GEE climate) 4. Harmonize spatial units → Admin 1 reference 5. Output analysis‑ready panel (mn_predictor_panel.parquet)

## Slide 12: Example: Predicting anemia in Ghana

## Slide 13
# Placeholder for anemia prediction code: # 1. fit SuperLearner # 2. cross-validated performance metrics

## Slide 14: Performance summary

## Slide 15
# TODO: knitr::kable(placeholder_table, caption = "Model performance comparison")

## Slide 16: Variable importance

## Slide 17
# TODO: ggplot variable importance bars grouped by domain

## Slide 18: Prediction map (Admin 1)

## Slide 19
# TODO: plot predicted anemia prevalence with terra::plot

## Slide 20: Uncertainty quantification

## Slide 21
# TODO: placeholder for bootstrap CI ribbon plot

## Slide 22: Next steps

## Slide 23
Finalize data landscape manuscript & submit (Journal of Global Health?)
Complete Ghana & Nigeria predictor panels
Launch modeler consortium > July 2025
Develop interactive dashboard (Shiny + leaflet)
Prepare Phase 2 funding report to Gates Foundation

## Slide 24: Discussion & feedback

## Slide 25
Are the predictor domains comprehensive?
Preferred visualization of uncertainty?
Suggestions for stakeholder engagement?

## Slide 26: Appendix

## Slide 27: Session info
sessionInfo()